## Summary
Okta to PingFederate SAML Migration Report
Customer | Customer
Generated (UTC) | 2026-09-27 16:17
Risk rules version | 2026.09-pf-2
Target | PingFederate (self-hosted)
Directory | AD
OGNL allowed | No
PingFederate base URL (assumed) | https://sso.example.com
PingFederate entity ID (assumed) | https://sso.example.com
Base URL and entity ID come from PF_BASE_URL / PF_ENTITY_ID in .env
Applications | SAML | OIDC
Applications
Blocked
Need access control (issuance criteria / policy)
Total assigned users
Overall level | SAML | OIDC
LOW
MEDIUM
HIGH
CRITICAL
Suggested wave | SAML | OIDC
Wave 0 (pilot)
Wave 1
Wave 2
Wave 3 (high impact)
Blocked
Decommission review
PingFederate build status | SAML | OIDC
Blocked
Ready to build
Built - differs
Built
Verified
Out of scope
Migration plan steps | SAML | OIDC
Not Started
In Progress
Done
Blocked
N/A
Okta vs PingFederate fields | SAML | OIDC
ACTION - Preparation required before migration
UNKNOWN - Not exposed by Okta's API - get from vendor
SP_UPDATE - Changes by design - update the SP at cutover
CONFIGURE - Standard PingFederate configuration
SAME - Carried over unchanged
N/A - Not used by this app

## Applications
Okta app ID | Application | Protocol | Type | Okta status | Migration state | Users | Direct users | Groups | Claims | Complexity score | Complexity | Impact score | Impact | Overall | Blocked | Blockers | Suggested wave | Assigned wave | Business owner | Criticality | Test env | Issuance criteria needed | OGNL values | Okta-only groups | LDAP attributes | Missing directory inputs | Critical | Warning | Info | Assessment | Assessment review | Reviewed by | PingFederate build | Plan steps done | Next plan step
0oa7employeeportal7 | Employee Portal | OIDC | Web | ACTIVE | DISCOVERED | 25 | 0 | 1 | 0 | 6 | MEDIUM | 5 | MEDIUM | MEDIUM | No | ' | Wave 1 | ' | ' | ' | Unknown | Yes | ' | ' | ' | ' | 0 | 2 | 4 | Not run | ' | ' | Built - differs | 0/7 | Prepare directory & decisions
0oa3engwiki00000003 | Engineering Wiki (Confluence DC) | SAML | Custom | ACTIVE | DISCOVERED | 10 | 0 | 3 | 4 | 20 | CRITICAL | 5 | MEDIUM | CRITICAL | Yes | CLAIM_NEEDS_OGNL | Blocked | ' | ' | ' | Unknown | Yes | fullName, wikiRole | ENG-Contractors | cn, department, givenName, mail, sn, userPrincipalName | ' | 2 | 5 | 6 | VALID | PENDING | ' | Built - differs | 0/7 | Prepare directory & decisions
0oa1expenseportal01 | Expense Portal | SAML | Custom | ACTIVE | DISCOVERED | 25 | 0 | 1 | 1 | 4 | LOW | 5 | MEDIUM | MEDIUM | Yes | DUPLICATE_SP_ENTITY_ID | Blocked | ' | ' | ' | Unknown | Yes | ' | ' | mail | ' | 0 | 2 | 2 | VALID | PENDING | ' | Built | 0/7 | Prepare directory & decisions
0oa1expenseuat00011 | Expense Portal (UAT) | SAML | Custom | ACTIVE | DISCOVERED | 5 | 0 | 1 | 1 | 6 | MEDIUM | 4 | MEDIUM | MEDIUM | Yes | DUPLICATE_SP_ENTITY_ID | Decommission review | ' | ' | ' | Unknown | Yes | ' | Finance | mail | ' | 0 | 4 | 1 | VALID | PENDING | ' | Built - differs | 0/7 | Prepare directory & decisions
0oa2hranalytics0002 | HR Analytics (Tableau) | SAML | Custom | ACTIVE | DISCOVERED | 5 | 2 | 1 | 7 | 15 | HIGH | 5 | MEDIUM | HIGH | Yes | CLAIM_NEEDS_OGNL | Blocked | ' | ' | ' | Unknown | Yes | displayName, username | HR-Analysts | employeeID, givenName, mail, sn, userPrincipalName | appuser.costCenter | 2 | 6 | 1 | VALID | PENDING | ' | Blocked | 0/7 | Prepare directory & decisions
0oa10legacyspa00010 | Legacy Intranet SPA | OIDC | Browser | ACTIVE | DISCOVERED | 9 | 1 | 1 | 0 | 11 | HIGH | 4 | MEDIUM | HIGH | No | ' | Decommission review | ' | ' | ' | Unknown | Yes | ' | Sales | ' | ' | 0 | 6 | 2 | Not run | ' | ' | Ready to build | 0/7 | Prepare directory & decisions
0oa6legacytravel006 | Legacy Travel Booking | SAML | Custom | INACTIVE | DISCOVERED | 0 | 0 | 0 | 1 | 5 | MEDIUM | 0 | LOW | MEDIUM | Yes | NAMEID_IS_OKTA_USER_ID | Decommission review | ' | ' | ' | Unknown | No | ' | ' | mail | user.id | 2 | 1 | 3 | VALID | PENDING | ' | Blocked | 0/7 | Prepare directory & decisions
0oa8mobileexpense08 | Mobile Expenses | OIDC | Native | ACTIVE | DISCOVERED | 5 | 0 | 1 | 0 | 6 | MEDIUM | 5 | MEDIUM | MEDIUM | No | ' | Wave 1 | ' | ' | ' | Unknown | Yes | ' | Finance | ' | ' | 0 | 2 | 3 | Not run | ' | ' | Ready to build | 0/7 | Prepare directory & decisions
0oa9reportingapi009 | Reporting API | OIDC | Service | ACTIVE | DISCOVERED | 0 | 0 | 0 | 0 | 2 | LOW | 4 | MEDIUM | MEDIUM | No | ' | Wave 1 | ' | ' | ' | Unknown | No | ' | ' | ' | ' | 0 | 0 | 4 | Not run | ' | ' | Built | 0/7 | Prepare directory & decisions
0oa5salesforce00005 | Salesforce | SAML | Catalog | ACTIVE | DISCOVERED | 8 | 0 | 1 | 0 | 10 | HIGH | 5 | MEDIUM | HIGH | No | ' | Wave 2 | ' | ' | ' | Unknown | Yes | ' | Sales | ' | ' | 0 | 4 | 0 | VALID | PENDING | ' | Ready to build | 0/7 | Prepare directory & decisions
0oa4servicenow00004 | ServiceNow | SAML | Catalog | ACTIVE | DISCOVERED | 12 | 0 | 2 | 0 | 8 | MEDIUM | 5 | MEDIUM | MEDIUM | No | ' | Wave 1 | ' | ' | ' | Unknown | Yes | ' | SN-Approvers, SN-ITIL | ' | ' | 0 | 3 | 0 | VALID | PENDING | ' | Built | 0/7 | Prepare directory & decisions

## SAML - Okta vs PingFederate
Application | Section | Field | Okta value | PingFederate setting | PingFederate value | Status | Note
Engineering Wiki (Confluence DC) | SP connection | Connection name | Engineering Wiki (Confluence DC) | SP Connection > General Info > Connection Name | Engineering Wiki (Confluence DC) | CONFIGURE | '
Engineering Wiki (Confluence DC) | SP connection | SP entity ID | https://wiki.northwind.example | Partner's Entity ID (Connection ID) | https://wiki.northwind.example | SAME | '
Engineering Wiki (Confluence DC) | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
Engineering Wiki (Confluence DC) | SP connection | ACS URL (index 0) | https://wiki.northwind.example/plugins/servlet/samlconsumer | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://wiki.northwind.example/plugins/servlet/samlconsumer | SAME | Set 'Default' on index 0
Engineering Wiki (Confluence DC) | SP connection | ACS URL (index 1) | https://wiki-dr.northwind.example/plugins/servlet/samlconsumer | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://wiki-dr.northwind.example/plugins/servlet/samlconsumer | SAME | '
Engineering Wiki (Confluence DC) | SP connection | Default RelayState | https://wiki.northwind.example/dashboard.action | IdP-initiated SSO TargetResource | https://wiki.northwind.example/dashboard.action | SAME | '
Engineering Wiki (Confluence DC) | SP connection | Single logout | Yes (https://wiki.northwind.example/plugins/servlet/samlslo) | Protocol Settings > SLO Service URL | https://wiki.northwind.example/plugins/servlet/samlslo | CONFIGURE | '
Engineering Wiki (Confluence DC) | SP connection | Signed AuthnRequests | Yes | Signature Verification > require signed AuthnRequests + SP certificate | Import SP signing certificate | CONFIGURE | '
Engineering Wiki (Confluence DC) | IdP identity | IdP entity ID (Issuer) | https://sso.northwind.example/wiki | Virtual Server ID on the connection | https://sso.northwind.example/wiki | ACTION | Add the custom issuer as a virtual server ID so the SP needs no change
Engineering Wiki (Confluence DC) | IdP identity | SSO URL | https://northwind.okta.com/app/northwind_engwiki_1/exk3engwiki00000003/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
Engineering Wiki (Confluence DC) | IdP identity | IdP-initiated SSO link | Okta app embed link | IdP-initiated SSO URL | https://sso.example.com/idp/startSSO.ping?PartnerSpId=https%3A%2F%2Fwiki.northwind.example | SP_UPDATE | Update portal bookmarks and links
Engineering Wiki (Confluence DC) | IdP identity | IdP metadata | Okta app metadata URL | Metadata export URL | https://sso.example.com/pf/federation_metadata.ping?PartnerSpId=https%3A%2F%2Fwiki.northwind.example | SP_UPDATE | '
Engineering Wiki (Confluence DC) | IdP identity | IdP SLO URL | Okta SLO endpoint | Runtime SLO endpoint | https://sso.example.com/idp/SLO.saml2 | SP_UPDATE | '
Engineering Wiki (Confluence DC) | IdP identity | Signing certificate | 8AAB226AFED6E2162ECAAA62A323DC594B34A5EB (expires 2028-01-15) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
Engineering Wiki (Confluence DC) | Assertion | NameID format | urn:oasis:names:tc:SAML:1.1:nameid-format:unspecified | Attribute Contract > SAML_SUBJECT format | urn:oasis:names:tc:SAML:1.1:nameid-format:unspecified | SAME | '
Engineering Wiki (Confluence DC) | Assertion | NameID value | ${user.login} | Contract Fulfillment > SAML_SUBJECT | LDAP: userPrincipalName | SAME | '
Engineering Wiki (Confluence DC) | Assertion | Signing | response + assertion | Signature Policy | Sign response + 'Always sign the SAML assertion' | CONFIGURE | '
Engineering Wiki (Confluence DC) | Assertion | Signature algorithm | RSA_SHA256 | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
Engineering Wiki (Confluence DC) | Assertion | AuthnContextClassRef | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | Authentication policy / adapter mapping | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | SAME | '
Engineering Wiki (Confluence DC) | Assertion | Assertion lifetime | 300 s | Protocol Settings > Assertion Lifetime (minutes before / after) | 5 / 5 | SAME | '
Engineering Wiki (Confluence DC) | Assertion | App username | ${source.login} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
Engineering Wiki (Confluence DC) | Attributes | email | user.email | Attribute Contract 'email' <- DATA_STORE | LDAP: mail | SAME | '
Engineering Wiki (Confluence DC) | Attributes | fullName | user.firstName + " " + user.lastName | Attribute Contract 'fullName' <- OGNL | OGNL needed (<concatenation>); LDAP inputs: givenName, sn | ACTION | '
Engineering Wiki (Confluence DC) | Attributes | wikiRole | user.department == "Engineering" ? "wiki-admin" : "wiki-user" | Attribute Contract 'wikiRole' <- OGNL | OGNL needed (<conditional>); LDAP inputs: department | ACTION | '
Engineering Wiki (Confluence DC) | Attributes | groups | REGEX ENG-.* | Attribute Contract 'groups' <- GROUP_LDAP_SEARCH | Chained LDAP attribute source returning cn, e.g. (&(objectClass=group)(member=<user DN>)(cn=ENG-*)) | ACTION | Okta-only groups: ENG-Contractors
Engineering Wiki (Confluence DC) | Access control | Assigned groups | ENG-Platform, ENG-Data, ENG-Mobile | Issuance Criteria (memberOf) | memberOf includes one of: ENG-Platform, ENG-Data, ENG-Mobile | ACTION | Without this, any authenticated user gets an assertion
Engineering Wiki (Confluence DC) | Access control | Assignment attributes | wikiSpace | Directory attribute or group-derived value | Store in the directory | ACTION | '
Expense Portal | SP connection | Connection name | Expense Portal | SP Connection > General Info > Connection Name | Expense Portal | CONFIGURE | '
Expense Portal | SP connection | SP entity ID | https://expenses.northwind.example | Partner's Entity ID (Connection ID) | https://expenses.northwind.example | ACTION | Shared with another Okta app - must be unique in PingFederate
Expense Portal | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
Expense Portal | SP connection | ACS URL (index 0) | https://expenses.northwind.example/saml/acs | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://expenses.northwind.example/saml/acs | SAME | '
Expense Portal | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
Expense Portal | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
Expense Portal | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
Expense Portal | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk1expenseportal01 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
Expense Portal | IdP identity | SSO URL | https://northwind.okta.com/app/northwind_expenseportal_1/exk1expenseportal01/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
Expense Portal | IdP identity | IdP-initiated SSO link | Okta app embed link | IdP-initiated SSO URL | https://sso.example.com/idp/startSSO.ping?PartnerSpId=https%3A%2F%2Fexpenses.northwind.example | SP_UPDATE | Update portal bookmarks and links
Expense Portal | IdP identity | IdP metadata | Okta app metadata URL | Metadata export URL | https://sso.example.com/pf/federation_metadata.ping?PartnerSpId=https%3A%2F%2Fexpenses.northwind.example | SP_UPDATE | '
Expense Portal | IdP identity | Signing certificate | 2AD29F582E4B19B50A193B33BDDCE3E5C9C420EF (expires 2029-06-01) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
Expense Portal | Assertion | NameID format | urn:oasis:names:tc:SAML:1.1:nameid-format:emailAddress | Attribute Contract > SAML_SUBJECT format | urn:oasis:names:tc:SAML:1.1:nameid-format:emailAddress | SAME | '
Expense Portal | Assertion | NameID value | ${user.email} | Contract Fulfillment > SAML_SUBJECT | LDAP: mail | SAME | '
Expense Portal | Assertion | Signing | response + assertion | Signature Policy | Sign response + 'Always sign the SAML assertion' | CONFIGURE | '
Expense Portal | Assertion | Signature algorithm | RSA_SHA256 | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
Expense Portal | Assertion | AuthnContextClassRef | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | Authentication policy / adapter mapping | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | SAME | '
Expense Portal | Assertion | Assertion lifetime | 300 s | Protocol Settings > Assertion Lifetime (minutes before / after) | 5 / 5 | SAME | '
Expense Portal | Assertion | App username | ${source.email} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
Expense Portal | Attributes | email | user.email | Attribute Contract 'email' <- DATA_STORE | LDAP: mail | SAME | '
Expense Portal | Access control | Assigned groups | All Employees | Issuance Criteria (memberOf) | memberOf includes one of: All Employees | ACTION | Without this, any authenticated user gets an assertion
Expense Portal (UAT) | SP connection | Connection name | Expense Portal (UAT) | SP Connection > General Info > Connection Name | Expense Portal (UAT) | CONFIGURE | '
Expense Portal (UAT) | SP connection | SP entity ID | https://expenses.northwind.example | Partner's Entity ID (Connection ID) | https://expenses.northwind.example | ACTION | Shared with another Okta app - must be unique in PingFederate
Expense Portal (UAT) | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
Expense Portal (UAT) | SP connection | ACS URL (index 0) | https://expenses-uat.northwind.example/saml/acs | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://expenses-uat.northwind.example/saml/acs | SAME | '
Expense Portal (UAT) | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
Expense Portal (UAT) | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
Expense Portal (UAT) | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
Expense Portal (UAT) | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk1expenseuat00011 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
Expense Portal (UAT) | IdP identity | SSO URL | https://northwind.okta.com/app/northwind_expenseportaluat_1/exk1expenseuat00011/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
Expense Portal (UAT) | IdP identity | IdP-initiated SSO link | Okta app embed link | IdP-initiated SSO URL | https://sso.example.com/idp/startSSO.ping?PartnerSpId=https%3A%2F%2Fexpenses.northwind.example | SP_UPDATE | Update portal bookmarks and links
Expense Portal (UAT) | IdP identity | IdP metadata | Okta app metadata URL | Metadata export URL | https://sso.example.com/pf/federation_metadata.ping?PartnerSpId=https%3A%2F%2Fexpenses.northwind.example | SP_UPDATE | '
Expense Portal (UAT) | IdP identity | Signing certificate | BF999BFA324FF03706A54F1D8837C408CC860D73 (expires 2029-06-01) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
Expense Portal (UAT) | Assertion | NameID format | urn:oasis:names:tc:SAML:1.1:nameid-format:emailAddress | Attribute Contract > SAML_SUBJECT format | urn:oasis:names:tc:SAML:1.1:nameid-format:emailAddress | SAME | '
Expense Portal (UAT) | Assertion | NameID value | ${user.email} | Contract Fulfillment > SAML_SUBJECT | LDAP: mail | SAME | '
Expense Portal (UAT) | Assertion | Signing | response + assertion | Signature Policy | Sign response + 'Always sign the SAML assertion' | CONFIGURE | '
Expense Portal (UAT) | Assertion | Signature algorithm | RSA_SHA256 | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
Expense Portal (UAT) | Assertion | AuthnContextClassRef | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | Authentication policy / adapter mapping | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | SAME | '
Expense Portal (UAT) | Assertion | Assertion lifetime | 300 s | Protocol Settings > Assertion Lifetime (minutes before / after) | 5 / 5 | SAME | '
Expense Portal (UAT) | Assertion | App username | ${source.email} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
Expense Portal (UAT) | Attributes | email | user.email | Attribute Contract 'email' <- DATA_STORE | LDAP: mail | SAME | '
Expense Portal (UAT) | Access control | Assigned groups | Finance | Issuance Criteria (memberOf) | memberOf includes one of: Finance | ACTION | Without this, any authenticated user gets an assertion
Expense Portal (UAT) | Access control | Okta-only groups | Finance | Directory groups | Create and populate in the directory | ACTION | '
HR Analytics (Tableau) | SP connection | Connection name | HR Analytics (Tableau) | SP Connection > General Info > Connection Name | HR Analytics (Tableau) | CONFIGURE | '
HR Analytics (Tableau) | SP connection | SP entity ID | https://tableau.northwind.example | Partner's Entity ID (Connection ID) | https://tableau.northwind.example | SAME | '
HR Analytics (Tableau) | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
HR Analytics (Tableau) | SP connection | ACS URL (index 0) | https://tableau.northwind.example/wg/saml/SSO/index.html | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://tableau.northwind.example/wg/saml/SSO/index.html | SAME | '
HR Analytics (Tableau) | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
HR Analytics (Tableau) | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
HR Analytics (Tableau) | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
HR Analytics (Tableau) | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk2hranalytics0002 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
HR Analytics (Tableau) | IdP identity | SSO URL | https://northwind.okta.com/app/northwind_hranalytics_1/exk2hranalytics0002/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
HR Analytics (Tableau) | IdP identity | IdP-initiated SSO link | Okta app embed link | IdP-initiated SSO URL | https://sso.example.com/idp/startSSO.ping?PartnerSpId=https%3A%2F%2Ftableau.northwind.example | SP_UPDATE | Update portal bookmarks and links
HR Analytics (Tableau) | IdP identity | IdP metadata | Okta app metadata URL | Metadata export URL | https://sso.example.com/pf/federation_metadata.ping?PartnerSpId=https%3A%2F%2Ftableau.northwind.example | SP_UPDATE | '
HR Analytics (Tableau) | IdP identity | Signing certificate | 51B9755BA24577173B960DE74436344DD4271F4A (expires 2026-11-11) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
HR Analytics (Tableau) | Assertion | NameID format | urn:oasis:names:tc:SAML:1.1:nameid-format:unspecified | Attribute Contract > SAML_SUBJECT format | urn:oasis:names:tc:SAML:1.1:nameid-format:unspecified | SAME | '
HR Analytics (Tableau) | Assertion | NameID value | ${user.userName} | Contract Fulfillment > SAML_SUBJECT | LDAP: userPrincipalName (via app username ${source.login}) | SAME | '
HR Analytics (Tableau) | Assertion | Signing | response + assertion | Signature Policy | Sign response + 'Always sign the SAML assertion' | CONFIGURE | '
HR Analytics (Tableau) | Assertion | Signature algorithm | RSA_SHA256 | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
HR Analytics (Tableau) | Assertion | AuthnContextClassRef | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | Authentication policy / adapter mapping | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | SAME | '
HR Analytics (Tableau) | Assertion | Assertion lifetime | 300 s | Protocol Settings > Assertion Lifetime (minutes before / after) | 5 / 5 | SAME | '
HR Analytics (Tableau) | Assertion | App username | ${source.login} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
HR Analytics (Tableau) | Attributes | firstName | user.firstName | Attribute Contract 'firstName' <- DATA_STORE | LDAP: givenName | SAME | '
HR Analytics (Tableau) | Attributes | lastName | user.lastName | Attribute Contract 'lastName' <- DATA_STORE | LDAP: sn | SAME | '
HR Analytics (Tableau) | Attributes | email | user.email | Attribute Contract 'email' <- DATA_STORE | LDAP: mail | SAME | '
HR Analytics (Tableau) | Attributes | employeeNumber | user.employeeNumber | Attribute Contract 'employeeNumber' <- DATA_STORE | LDAP: employeeID | SAME | '
HR Analytics (Tableau) | Attributes | displayName | user.firstName + " " + user.lastName | Attribute Contract 'displayName' <- OGNL | OGNL needed (<concatenation>); LDAP inputs: givenName, sn | ACTION | '
HR Analytics (Tableau) | Attributes | username | String.substringBefore(user.login, "@") | Attribute Contract 'username' <- OGNL | OGNL needed (String.substringBefore); LDAP inputs: userPrincipalName | ACTION | '
HR Analytics (Tableau) | Attributes | costCenter | appuser.costCenter | Attribute Contract 'costCenter' <- APPUSER | appuser.costCenter is an Okta app-user attribute; it must be stored in the directory (or derived from groups) first | ACTION | '
HR Analytics (Tableau) | Access control | Assigned groups | HR-Analysts | Issuance Criteria (memberOf) | memberOf includes one of: HR-Analysts | ACTION | Without this, any authenticated user gets an assertion
HR Analytics (Tableau) | Access control | Direct user assignments | 2 user(s) | Issuance Criteria | Put users in a directory group | ACTION | '
HR Analytics (Tableau) | Access control | Okta-only groups | HR-Analysts | Directory groups | Create and populate in the directory | ACTION | '
HR Analytics (Tableau) | Access control | Assignment attributes | costCenter | Directory attribute or group-derived value | Store in the directory | ACTION | '
Legacy Travel Booking | SP connection | Connection name | Legacy Travel Booking | SP Connection > General Info > Connection Name | Legacy Travel Booking | CONFIGURE | '
Legacy Travel Booking | SP connection | SP entity ID | urn:northwind:travel | Partner's Entity ID (Connection ID) | urn:northwind:travel | SAME | '
Legacy Travel Booking | SP connection | Okta app status | INACTIVE | Connection status | Create disabled or skip | ACTION | '
Legacy Travel Booking | SP connection | ACS URL (index 0) | https://travel-old.northwind.example/sso/acs | Protocol Settings > Assertion Consumer Service URL (HTTP-POST) | https://travel-old.northwind.example/sso/acs | SAME | '
Legacy Travel Booking | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
Legacy Travel Booking | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
Legacy Travel Booking | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
Legacy Travel Booking | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk6legacytravel006 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
Legacy Travel Booking | IdP identity | SSO URL | https://northwind.okta.com/app/northwind_legacytravel_1/exk6legacytravel006/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
Legacy Travel Booking | IdP identity | IdP-initiated SSO link | Okta app embed link | IdP-initiated SSO URL | https://sso.example.com/idp/startSSO.ping?PartnerSpId=urn%3Anorthwind%3Atravel | SP_UPDATE | Update portal bookmarks and links
Legacy Travel Booking | IdP identity | IdP metadata | Okta app metadata URL | Metadata export URL | https://sso.example.com/pf/federation_metadata.ping?PartnerSpId=urn%3Anorthwind%3Atravel | SP_UPDATE | '
Legacy Travel Booking | IdP identity | Signing certificate | DED99A458EB1C45D4A5DD8598A1665932E146399 (expires 2026-03-01) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
Legacy Travel Booking | Assertion | NameID format | urn:oasis:names:tc:SAML:2.0:nameid-format:persistent | Attribute Contract > SAML_SUBJECT format | urn:oasis:names:tc:SAML:2.0:nameid-format:persistent | SAME | '
Legacy Travel Booking | Assertion | NameID value | ${user.id} | Contract Fulfillment > SAML_SUBJECT | Okta user id: not present in any directory | ACTION | '
Legacy Travel Booking | Assertion | Signing | response + assertion | Signature Policy | Sign response + 'Always sign the SAML assertion' | CONFIGURE | '
Legacy Travel Booking | Assertion | Signature algorithm | RSA_SHA1 | Signature Policy > Signing Algorithm | RSA SHA1 (plan SHA256) | ACTION | '
Legacy Travel Booking | Assertion | AuthnContextClassRef | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | Authentication policy / adapter mapping | urn:oasis:names:tc:SAML:2.0:ac:classes:PasswordProtectedTransport | SAME | '
Legacy Travel Booking | Assertion | Assertion lifetime | 300 s | Protocol Settings > Assertion Lifetime (minutes before / after) | 5 / 5 | SAME | '
Legacy Travel Booking | Assertion | App username | ${source.login} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
Legacy Travel Booking | Attributes | mail | user.email | Attribute Contract 'mail' <- DATA_STORE | LDAP: mail | SAME | '
Legacy Travel Booking | Access control | Assigned groups | — | Issuance Criteria | — | N/A | '
Salesforce | SP connection | Connection name | Salesforce | SP Connection > General Info > Connection Name | Salesforce | CONFIGURE | '
Salesforce | SP connection | SP entity ID | Not exposed (catalog app) | Partner's Entity ID (Connection ID) | From vendor SP metadata | UNKNOWN | Import the SP metadata to fill this in
Salesforce | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
Salesforce | SP connection | ACS URL | Not exposed (catalog app) | Protocol Settings > Assertion Consumer Service URL | From vendor SP metadata | UNKNOWN | '
Salesforce | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
Salesforce | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
Salesforce | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
Salesforce | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk5salesforce00005 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
Salesforce | IdP identity | SSO URL | https://northwind.okta.com/app/salesforce/exk5salesforce00005/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
Salesforce | IdP identity | Signing certificate | 38F45087D6987CED4F0B18DBDA88DF8FD760F8E7 (expires 2028-08-01) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
Salesforce | Assertion | NameID format | — | Attribute Contract > SAML_SUBJECT format | — | UNKNOWN | '
Salesforce | Assertion | NameID value | — | Contract Fulfillment > SAML_SUBJECT | No NameID template visible (catalog app) | UNKNOWN | '
Salesforce | Assertion | Signing | — | Signature Policy | Sign response (default) | SAME | '
Salesforce | Assertion | Signature algorithm | — | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
Salesforce | Assertion | AuthnContextClassRef | — | Authentication policy / adapter mapping | — | SAME | '
Salesforce | Assertion | App username | ${source.employeeNumber}@northwind.sfdc | Used via SAML_SUBJECT / attributes | Needs directory attribute or OGNL | ACTION | '
Salesforce | Attributes | Attribute statements | Not exposed (catalog app) | Attribute Contract | From vendor documentation | UNKNOWN | '
Salesforce | Access control | Assigned groups | Sales | Issuance Criteria (memberOf) | memberOf includes one of: Sales | ACTION | Without this, any authenticated user gets an assertion
Salesforce | Access control | Okta-only groups | Sales | Directory groups | Create and populate in the directory | ACTION | '
ServiceNow | SP connection | Connection name | ServiceNow | SP Connection > General Info > Connection Name | ServiceNow | CONFIGURE | '
ServiceNow | SP connection | SP entity ID | Not exposed (catalog app) | Partner's Entity ID (Connection ID) | From vendor SP metadata | UNKNOWN | Import the SP metadata to fill this in
ServiceNow | SP connection | Okta app status | ACTIVE | Connection status | Active | SAME | '
ServiceNow | SP connection | ACS URL | Not exposed (catalog app) | Protocol Settings > Assertion Consumer Service URL | From vendor SP metadata | UNKNOWN | '
ServiceNow | SP connection | Default RelayState | — | IdP-initiated SSO TargetResource | — | N/A | '
ServiceNow | SP connection | Single logout | No | Protocol Settings > SLO Service URL | — | N/A | '
ServiceNow | SP connection | Signed AuthnRequests | No | Signature Verification > require signed AuthnRequests + SP certificate | Not required | N/A | '
ServiceNow | IdP identity | IdP entity ID (Issuer) | http://www.okta.com/exk4servicenow00004 | Server Settings > SAML 2.0 Entity ID | https://sso.example.com | SP_UPDATE | SP must trust the new issuer
ServiceNow | IdP identity | SSO URL | https://northwind.okta.com/app/servicenow_ud/exk4servicenow00004/sso/saml | Runtime SSO endpoint | https://sso.example.com/idp/SSO.saml2 | SP_UPDATE | '
ServiceNow | IdP identity | Signing certificate | 851CB8360434754B37888C97B31228B8EFF0C276 (expires 2028-03-01) | Signature Policy > Signing Certificate | PingFederate signing key (new) | SP_UPDATE | Okta does not export private keys - SP must trust the new certificate
ServiceNow | Assertion | NameID format | — | Attribute Contract > SAML_SUBJECT format | — | UNKNOWN | '
ServiceNow | Assertion | NameID value | — | Contract Fulfillment > SAML_SUBJECT | No NameID template visible (catalog app) | UNKNOWN | '
ServiceNow | Assertion | Signing | — | Signature Policy | Sign response (default) | SAME | '
ServiceNow | Assertion | Signature algorithm | — | Signature Policy > Signing Algorithm | RSA SHA256 | SAME | '
ServiceNow | Assertion | AuthnContextClassRef | — | Authentication policy / adapter mapping | — | SAME | '
ServiceNow | Assertion | App username | ${source.email} | Used via SAML_SUBJECT / attributes | Directory attribute | SAME | '
ServiceNow | Attributes | Attribute statements | Not exposed (catalog app) | Attribute Contract | From vendor documentation | UNKNOWN | '
ServiceNow | Access control | Assigned groups | SN-ITIL, SN-Approvers | Issuance Criteria (memberOf) | memberOf includes one of: SN-ITIL, SN-Approvers | ACTION | Without this, any authenticated user gets an assertion
ServiceNow | Access control | Okta-only groups | SN-ITIL, SN-Approvers | Directory groups | Create and populate in the directory | ACTION | '

## OIDC - Okta vs PingFederate
Application | Section | Field | Okta value | PingFederate setting | PingFederate value | Status | Note
Employee Portal | OAuth client | Client name | Employee Portal | OAuth Client > Name | Employee Portal | CONFIGURE | '
Employee Portal | OAuth client | Client ID | 0oa7EmpPortalClient01 | OAuth Client > Client ID | 0oa7EmpPortalClient01 | SAME | PingFederate lets you keep the same client ID, so the app config for it does not change
Employee Portal | OAuth client | Application type | web | Client type (derived) | Confidential client (web app) | CONFIGURE | '
Employee Portal | OAuth client | Client authentication | client_secret_basic | Client Authentication | Client Secret (HTTP Basic) - new secret | ACTION | Okta does not return existing secrets; issue a new one and update the app
Employee Portal | OAuth client | Okta app status | ACTIVE | Client status | Enabled | SAME | '
Employee Portal | OAuth client | Consent | TRUSTED | Bypass Authorization Approval | Bypass (trusted) | SAME | '
Employee Portal | Redirects | Redirect URI 1 | https://portal.northwind.example/callback | Redirect URIs | https://portal.northwind.example/callback | SAME | '
Employee Portal | Redirects | Redirect URI 2 | https://portal.northwind.example/silent-renew | Redirect URIs | https://portal.northwind.example/silent-renew | SAME | '
Employee Portal | Redirects | Post-logout redirect 1 | https://portal.northwind.example/ | Logout URIs | https://portal.northwind.example/ | SAME | '
Employee Portal | Redirects | Initiate login URI | https://portal.northwind.example/login | Portal / launcher link | https://portal.northwind.example/login | CONFIGURE | Use in your app launcher; PingFederate does not start OIDC logins itself
Employee Portal | Grants & tokens | Grant: authorization_code | authorization_code | Allowed Grant Types | Authorization Code | SAME | '
Employee Portal | Grants & tokens | Grant: refresh_token | refresh_token | Allowed Grant Types | Refresh Token | SAME | '
Employee Portal | Grants & tokens | Response types | code | Restrict Response Types | code | CONFIGURE | '
Employee Portal | Grants & tokens | PKCE | No | Require Proof Key for Code Exchange (PKCE) | Optional | SAME | '
Employee Portal | Grants & tokens | Existing refresh tokens | Issued by Okta | Refresh tokens | Not migrated - users sign in once after cutover | SP_UPDATE | '
Employee Portal | Grants & tokens | Access token format / lifetime | Set on the Okta authorization server | Access Token Manager | To be defined (next sprint) | UNKNOWN | '
Employee Portal | Endpoints | Issuer | https://<okta-org>/oauth2/<auth-server> | PingFederate runtime | https://sso.example.com | SP_UPDATE | Apps using the discovery document pick the rest up automatically
Employee Portal | Endpoints | Discovery document | https://<okta-org>/oauth2/<auth-server>/.well-known/openid-configuration | PingFederate runtime | https://sso.example.com/.well-known/openid-configuration | SP_UPDATE | '
Employee Portal | Endpoints | Authorization endpoint | https://<okta-org>/oauth2/<auth-server>/v1/authorize | PingFederate runtime | https://sso.example.com/as/authorization.oauth2 | SP_UPDATE | '
Employee Portal | Endpoints | Token endpoint | https://<okta-org>/oauth2/<auth-server>/v1/token | PingFederate runtime | https://sso.example.com/as/token.oauth2 | SP_UPDATE | '
Employee Portal | Endpoints | UserInfo endpoint | https://<okta-org>/oauth2/<auth-server>/v1/userinfo | PingFederate runtime | https://sso.example.com/idp/userinfo.openid | SP_UPDATE | '
Employee Portal | Endpoints | JWKS (signing keys) | https://<okta-org>/oauth2/<auth-server>/v1/keys | PingFederate runtime | https://sso.example.com/pf/JWKS | SP_UPDATE | '
Employee Portal | Endpoints | Logout endpoint | https://<okta-org>/oauth2/<auth-server>/v1/logout | PingFederate runtime | https://sso.example.com/idp/startSLO.ping | SP_UPDATE | '
Employee Portal | Scopes & claims | Scopes | Granted by the Okta authorization server policy | OAuth scopes / scope groups | Analysed next sprint | UNKNOWN | '
Employee Portal | Scopes & claims | ID token claims | Okta authorization server claims | OpenID Connect policy | Analysed next sprint | UNKNOWN | '
Employee Portal | Scopes & claims | Access token claims | Okta authorization server claims | Access token mapping | Analysed next sprint | UNKNOWN | '
Employee Portal | Access control | Assigned groups | All Employees | Authentication policy / issuance criteria | memberOf includes one of: All Employees | ACTION | Without this, any user who can sign in gets tokens
Legacy Intranet SPA | OAuth client | Client name | Legacy Intranet SPA | OAuth Client > Name | Legacy Intranet SPA | CONFIGURE | '
Legacy Intranet SPA | OAuth client | Client ID | 0oa10LegacySpaClnt10 | OAuth Client > Client ID | 0oa10LegacySpaClnt10 | SAME | PingFederate lets you keep the same client ID, so the app config for it does not change
Legacy Intranet SPA | OAuth client | Application type | browser | Client type (derived) | Public client (single-page app) | CONFIGURE | '
Legacy Intranet SPA | OAuth client | Client authentication | none | Client Authentication | None (public client) | SAME | '
Legacy Intranet SPA | OAuth client | Okta app status | ACTIVE | Client status | Enabled | SAME | '
Legacy Intranet SPA | OAuth client | Consent | TRUSTED | Bypass Authorization Approval | Bypass (trusted) | SAME | '
Legacy Intranet SPA | Redirects | Redirect URI 1 | https://intranet.northwind.example/* | Redirect URIs | https://intranet.northwind.example/* | ACTION | Wildcard: confirm PingFederate matching
Legacy Intranet SPA | Redirects | Redirect URI 2 | https://intranet-old.northwind.example/auth | Redirect URIs | https://intranet-old.northwind.example/auth | SAME | '
Legacy Intranet SPA | Grants & tokens | Grant: implicit | implicit | Allowed Grant Types | Implicit | ACTION | Deprecated - move to Authorization Code + PKCE
Legacy Intranet SPA | Grants & tokens | Response types | id_token, token | Restrict Response Types | id_token, token | CONFIGURE | '
Legacy Intranet SPA | Grants & tokens | Access token format / lifetime | Set on the Okta authorization server | Access Token Manager | To be defined (next sprint) | UNKNOWN | '
Legacy Intranet SPA | Endpoints | Issuer | https://<okta-org>/oauth2/<auth-server> | PingFederate runtime | https://sso.example.com | SP_UPDATE | Apps using the discovery document pick the rest up automatically
Legacy Intranet SPA | Endpoints | Discovery document | https://<okta-org>/oauth2/<auth-server>/.well-known/openid-configuration | PingFederate runtime | https://sso.example.com/.well-known/openid-configuration | SP_UPDATE | '
Legacy Intranet SPA | Endpoints | Authorization endpoint | https://<okta-org>/oauth2/<auth-server>/v1/authorize | PingFederate runtime | https://sso.example.com/as/authorization.oauth2 | SP_UPDATE | '
Legacy Intranet SPA | Endpoints | Token endpoint | https://<okta-org>/oauth2/<auth-server>/v1/token | PingFederate runtime | https://sso.example.com/as/token.oauth2 | SP_UPDATE | '
Legacy Intranet SPA | Endpoints | UserInfo endpoint | https://<okta-org>/oauth2/<auth-server>/v1/userinfo | PingFederate runtime | https://sso.example.com/idp/userinfo.openid | SP_UPDATE | '
Legacy Intranet SPA | Endpoints | JWKS (signing keys) | https://<okta-org>/oauth2/<auth-server>/v1/keys | PingFederate runtime | https://sso.example.com/pf/JWKS | SP_UPDATE | '
Legacy Intranet SPA | Scopes & claims | Scopes | Granted by the Okta authorization server policy | OAuth scopes / scope groups | Analysed next sprint | UNKNOWN | '
Legacy Intranet SPA | Scopes & claims | ID token claims | Okta authorization server claims | OpenID Connect policy | Analysed next sprint | UNKNOWN | '
Legacy Intranet SPA | Scopes & claims | Access token claims | Okta authorization server claims | Access token mapping | Analysed next sprint | UNKNOWN | '
Legacy Intranet SPA | Access control | Assigned groups | Sales | Authentication policy / issuance criteria | memberOf includes one of: Sales | ACTION | Without this, any user who can sign in gets tokens
Legacy Intranet SPA | Access control | Direct user assignments | 1 user(s) | Authentication policy | Put users in a directory group | ACTION | '
Legacy Intranet SPA | Access control | Okta-only groups | Sales | Directory groups | Create and populate in the directory | ACTION | '
Mobile Expenses | OAuth client | Client name | Mobile Expenses | OAuth Client > Name | Mobile Expenses | CONFIGURE | '
Mobile Expenses | OAuth client | Client ID | 0oa8MobileExpClient08 | OAuth Client > Client ID | 0oa8MobileExpClient08 | SAME | PingFederate lets you keep the same client ID, so the app config for it does not change
Mobile Expenses | OAuth client | Application type | native | Client type (derived) | Public client (native / mobile) | CONFIGURE | '
Mobile Expenses | OAuth client | Client authentication | none | Client Authentication | None (public client) | SAME | '
Mobile Expenses | OAuth client | Okta app status | ACTIVE | Client status | Enabled | SAME | '
Mobile Expenses | OAuth client | Consent | TRUSTED | Bypass Authorization Approval | Bypass (trusted) | SAME | '
Mobile Expenses | Redirects | Redirect URI 1 | com.northwind.expenses:/callback | Redirect URIs | com.northwind.expenses:/callback | SAME | '
Mobile Expenses | Grants & tokens | Grant: authorization_code | authorization_code | Allowed Grant Types | Authorization Code | SAME | '
Mobile Expenses | Grants & tokens | Grant: refresh_token | refresh_token | Allowed Grant Types | Refresh Token | SAME | '
Mobile Expenses | Grants & tokens | Response types | code | Restrict Response Types | code | CONFIGURE | '
Mobile Expenses | Grants & tokens | PKCE | Yes | Require Proof Key for Code Exchange (PKCE) | Yes | SAME | '
Mobile Expenses | Grants & tokens | Existing refresh tokens | Issued by Okta | Refresh tokens | Not migrated - users sign in once after cutover | SP_UPDATE | '
Mobile Expenses | Grants & tokens | Access token format / lifetime | Set on the Okta authorization server | Access Token Manager | To be defined (next sprint) | UNKNOWN | '
Mobile Expenses | Endpoints | Issuer | https://<okta-org>/oauth2/<auth-server> | PingFederate runtime | https://sso.example.com | SP_UPDATE | Apps using the discovery document pick the rest up automatically
Mobile Expenses | Endpoints | Discovery document | https://<okta-org>/oauth2/<auth-server>/.well-known/openid-configuration | PingFederate runtime | https://sso.example.com/.well-known/openid-configuration | SP_UPDATE | '
Mobile Expenses | Endpoints | Authorization endpoint | https://<okta-org>/oauth2/<auth-server>/v1/authorize | PingFederate runtime | https://sso.example.com/as/authorization.oauth2 | SP_UPDATE | '
Mobile Expenses | Endpoints | Token endpoint | https://<okta-org>/oauth2/<auth-server>/v1/token | PingFederate runtime | https://sso.example.com/as/token.oauth2 | SP_UPDATE | '
Mobile Expenses | Endpoints | UserInfo endpoint | https://<okta-org>/oauth2/<auth-server>/v1/userinfo | PingFederate runtime | https://sso.example.com/idp/userinfo.openid | SP_UPDATE | '
Mobile Expenses | Endpoints | JWKS (signing keys) | https://<okta-org>/oauth2/<auth-server>/v1/keys | PingFederate runtime | https://sso.example.com/pf/JWKS | SP_UPDATE | '
Mobile Expenses | Scopes & claims | Scopes | Granted by the Okta authorization server policy | OAuth scopes / scope groups | Analysed next sprint | UNKNOWN | '
Mobile Expenses | Scopes & claims | ID token claims | Okta authorization server claims | OpenID Connect policy | Analysed next sprint | UNKNOWN | '
Mobile Expenses | Scopes & claims | Access token claims | Okta authorization server claims | Access token mapping | Analysed next sprint | UNKNOWN | '
Mobile Expenses | Access control | Assigned groups | Finance | Authentication policy / issuance criteria | memberOf includes one of: Finance | ACTION | Without this, any user who can sign in gets tokens
Mobile Expenses | Access control | Okta-only groups | Finance | Directory groups | Create and populate in the directory | ACTION | '
Reporting API | OAuth client | Client name | Reporting API | OAuth Client > Name | Reporting API | CONFIGURE | '
Reporting API | OAuth client | Client ID | 0oa9ReportingSvc0009 | OAuth Client > Client ID | 0oa9ReportingSvc0009 | SAME | PingFederate lets you keep the same client ID, so the app config for it does not change
Reporting API | OAuth client | Application type | service | Client type (derived) | Confidential client (machine-to-machine) | CONFIGURE | '
Reporting API | OAuth client | Client authentication | private_key_jwt | Client Authentication | Private Key JWT (import the client's JWKS) | CONFIGURE | No secret changes
Reporting API | OAuth client | Okta app status | ACTIVE | Client status | Enabled | SAME | '
Reporting API | OAuth client | Consent | TRUSTED | Bypass Authorization Approval | Bypass (trusted) | SAME | '
Reporting API | Redirects | Redirect URIs | — | Redirect URIs | — | N/A | '
Reporting API | Grants & tokens | Grant: client_credentials | client_credentials | Allowed Grant Types | Client Credentials | SAME | '
Reporting API | Grants & tokens | Response types | token | Restrict Response Types | token | CONFIGURE | '
Reporting API | Grants & tokens | Access token format / lifetime | Set on the Okta authorization server | Access Token Manager | To be defined (next sprint) | UNKNOWN | '
Reporting API | Endpoints | Issuer | https://<okta-org>/oauth2/<auth-server> | PingFederate runtime | https://sso.example.com | SP_UPDATE | Apps using the discovery document pick the rest up automatically
Reporting API | Endpoints | Discovery document | https://<okta-org>/oauth2/<auth-server>/.well-known/openid-configuration | PingFederate runtime | https://sso.example.com/.well-known/openid-configuration | SP_UPDATE | '
Reporting API | Endpoints | Token endpoint | https://<okta-org>/oauth2/<auth-server>/v1/token | PingFederate runtime | https://sso.example.com/as/token.oauth2 | SP_UPDATE | '
Reporting API | Endpoints | JWKS (signing keys) | https://<okta-org>/oauth2/<auth-server>/v1/keys | PingFederate runtime | https://sso.example.com/pf/JWKS | SP_UPDATE | '
Reporting API | Scopes & claims | Scopes | Granted by the Okta authorization server policy | OAuth scopes / scope groups | Analysed next sprint | UNKNOWN | '
Reporting API | Scopes & claims | Access token claims | Okta authorization server claims | Access token mapping | Analysed next sprint | UNKNOWN | '
Reporting API | Access control | Who can use it | Machine client (no users) | Client credentials only | Restrict by client and scopes | CONFIGURE | '

## PingFederate reconciliation
Okta app | Protocol | PingFederate object | Matched by | Check | Expected (Okta) | Actual (PingFederate) | Result
Employee Portal | OIDC | Employee Portal | client ID | Redirect URIs | https://portal.northwind.example/callback, https://portal.northwind.example/silent-renew | https://portal.northwind.example/callback | DIFFERS
Employee Portal | OIDC | Employee Portal | client ID | Grant types | authorization_code, refresh_token | authorization_code, refresh_token | OK
Employee Portal | OIDC | Employee Portal | client ID | Client authentication | client_secret | client_secret | OK
Employee Portal | OIDC | Employee Portal | client ID | Access control | Authentication policy / issuance criteria | Verify in PingFederate policies (not on the client) | OK
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | ACS URLs | https://wiki-dr.northwind.example/plugins/servlet/samlconsumer, https://wiki.northwind.example/plugins/servlet/samlconsumer | https://wiki.northwind.example/plugins/servlet/samlconsumer | DIFFERS
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | Attribute contract | SAML_SUBJECT, email, fullName, groups, wikiRole | SAML_SUBJECT, email, fullName, groups (missing: wikiRole) | DIFFERS
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | Sign assertion | Yes | Yes | OK
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | Virtual server ID | https://sso.northwind.example/wiki | — | DIFFERS
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | Issuance criteria (access control) | Required | None | DIFFERS
Engineering Wiki (Confluence DC) | SAML | Engineering Wiki (Confluence DC) | entity ID | Single logout | https://wiki.northwind.example/plugins/servlet/samlslo | — | DIFFERS
Expense Portal | SAML | Expense Portal | entity ID | ACS URLs | https://expenses.northwind.example/saml/acs | https://expenses.northwind.example/saml/acs | OK
Expense Portal | SAML | Expense Portal | entity ID | Attribute contract | SAML_SUBJECT, email | SAML_SUBJECT, email | OK
Expense Portal | SAML | Expense Portal | entity ID | Sign assertion | Yes | Yes | OK
Expense Portal | SAML | Expense Portal | entity ID | Issuance criteria (access control) | Required | Present | OK
Expense Portal (UAT) | SAML | Expense Portal | entity ID | Own SP connection | A separate connection for this app | Already used by Expense Portal | DIFFERS
HR Analytics (Tableau) | SAML | ' | ' | Exists on PingFederate | Yes | Not found | NOT BUILT
Legacy Intranet SPA | OIDC | ' | ' | Exists on PingFederate | Yes | Not found | NOT BUILT
Legacy Travel Booking | SAML | ' | ' | Exists on PingFederate | Yes | Not found | NOT BUILT
Mobile Expenses | OIDC | ' | ' | Exists on PingFederate | Yes | Not found | NOT BUILT
Reporting API | OIDC | Reporting API | client ID | Grant types | client_credentials | client_credentials | OK
Reporting API | OIDC | Reporting API | client ID | Client authentication | private_key_jwt | private_key_jwt | OK
Reporting API | OIDC | Reporting API | client ID | Access control | Authentication policy / issuance criteria | Verify in PingFederate policies (not on the client) | OK
Salesforce | SAML | ' | ' | Exists on PingFederate | Yes | Not found | NOT BUILT
ServiceNow | SAML | ServiceNow | name | Attribute contract | SAML_SUBJECT | SAML_SUBJECT | OK
ServiceNow | SAML | ServiceNow | name | Issuance criteria (access control) | Required | Present | OK

## Migration plan
Application | Protocol | Wave | # | Step | Status | Owner | Due date | Notes | Updated by | PingFederate build
Employee Portal | OIDC | Wave 1 | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 6 | Verify | Not Started | App owner |  | ' | ' | Built - differs
Employee Portal | OIDC | Wave 1 | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 6 | Verify | Not Started | App owner |  | ' | ' | Built - differs
Engineering Wiki (Confluence DC) | SAML | Blocked | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built - differs
Expense Portal | SAML | Blocked | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built
Expense Portal | SAML | Blocked | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built
Expense Portal | SAML | Blocked | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built
Expense Portal | SAML | Blocked | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built
Expense Portal | SAML | Blocked | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built
Expense Portal | SAML | Blocked | 6 | Verify | Not Started | App owner |  | ' | ' | Built
Expense Portal | SAML | Blocked | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built
Expense Portal (UAT) | SAML | Decommission review | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 6 | Verify | Not Started | App owner |  | ' | ' | Built - differs
Expense Portal (UAT) | SAML | Decommission review | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built - differs
HR Analytics (Tableau) | SAML | Blocked | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 6 | Verify | Not Started | App owner |  | ' | ' | Blocked
HR Analytics (Tableau) | SAML | Blocked | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Blocked
Legacy Intranet SPA | OIDC | Decommission review | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 6 | Verify | Not Started | App owner |  | ' | ' | Ready to build
Legacy Intranet SPA | OIDC | Decommission review | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Ready to build
Legacy Travel Booking | SAML | Decommission review | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 6 | Verify | Not Started | App owner |  | ' | ' | Blocked
Legacy Travel Booking | SAML | Decommission review | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Blocked
Mobile Expenses | OIDC | Wave 1 | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 6 | Verify | Not Started | App owner |  | ' | ' | Ready to build
Mobile Expenses | OIDC | Wave 1 | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Ready to build
Reporting API | OIDC | Wave 1 | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 6 | Verify | Not Started | App owner |  | ' | ' | Built
Reporting API | OIDC | Wave 1 | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built
Salesforce | SAML | Wave 2 | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 6 | Verify | Not Started | App owner |  | ' | ' | Ready to build
Salesforce | SAML | Wave 2 | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Ready to build
ServiceNow | SAML | Wave 1 | 1 | Prepare directory & decisions | Not Started | Directory team |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 2 | Build in PingFederate | Not Started | IAM team |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 3 | Test with pilot users | Not Started | IAM team |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 4 | Update the SP / app | Not Started | App owner |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 5 | Cutover | Not Started | IAM team + App owner |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 6 | Verify | Not Started | App owner |  | ' | ' | Built
ServiceNow | SAML | Wave 1 | 7 | Remove from Okta | Not Started | IAM team |  | ' | ' | Built

## Attribute mapping
Application | Attribute | Type | Okta value / filter | Okta classification | PingFederate source | PingFederate detail | LDAP attributes | Missing inputs | Okta-only groups
Engineering Wiki (Confluence DC) | email | EXPRESSION | user.email | DIRECT | DATA_STORE | LDAP: mail | mail | ' | '
Engineering Wiki (Confluence DC) | fullName | EXPRESSION | user.firstName + " " + user.lastName | COMPLEX | OGNL | OGNL needed (<concatenation>); LDAP inputs: givenName, sn | givenName, sn | ' | '
Engineering Wiki (Confluence DC) | wikiRole | EXPRESSION | user.department == "Engineering" ? "wiki-admin" : "wiki-user" | COMPLEX | OGNL | OGNL needed (<conditional>); LDAP inputs: department | department | ' | '
Engineering Wiki (Confluence DC) | groups | GROUP | REGEX ENG-.* | GROUP | GROUP_LDAP_SEARCH | Chained LDAP attribute source returning cn, e.g. (&(objectClass=group)(member=<user DN>)(cn=ENG-*)) | cn | ' | ENG-Contractors
Expense Portal | email | EXPRESSION | user.email | DIRECT | DATA_STORE | LDAP: mail | mail | ' | '
Expense Portal (UAT) | email | EXPRESSION | user.email | DIRECT | DATA_STORE | LDAP: mail | mail | ' | '
HR Analytics (Tableau) | firstName | EXPRESSION | user.firstName | DIRECT | DATA_STORE | LDAP: givenName | givenName | ' | '
HR Analytics (Tableau) | lastName | EXPRESSION | user.lastName | DIRECT | DATA_STORE | LDAP: sn | sn | ' | '
HR Analytics (Tableau) | email | EXPRESSION | user.email | DIRECT | DATA_STORE | LDAP: mail | mail | ' | '
HR Analytics (Tableau) | employeeNumber | EXPRESSION | user.employeeNumber | DIRECT | DATA_STORE | LDAP: employeeID | employeeID | ' | '
HR Analytics (Tableau) | displayName | EXPRESSION | user.firstName + " " + user.lastName | COMPLEX | OGNL | OGNL needed (<concatenation>); LDAP inputs: givenName, sn | givenName, sn | ' | '
HR Analytics (Tableau) | username | EXPRESSION | String.substringBefore(user.login, "@") | COMPLEX | OGNL | OGNL needed (String.substringBefore); LDAP inputs: userPrincipalName | userPrincipalName | ' | '
HR Analytics (Tableau) | costCenter | EXPRESSION | appuser.costCenter | DIRECT | APPUSER | appuser.costCenter is an Okta app-user attribute; it must be stored in the directory (or derived from groups) first | ' | appuser.costCenter | '
Legacy Travel Booking | mail | EXPRESSION | user.email | DIRECT | DATA_STORE | LDAP: mail | mail | ' | '

## Directory prep
Item | Name | Apps affected | Applications
Group to create | ENG-Contractors | 1 | Engineering Wiki (Confluence DC)
Group to create | Finance | 2 | Expense Portal (UAT), Mobile Expenses
Group to create | HR-Analysts | 1 | HR Analytics (Tableau)
Group to create | SN-Approvers | 1 | ServiceNow
Group to create | SN-ITIL | 1 | ServiceNow
Group to create | Sales | 2 | Legacy Intranet SPA, Salesforce
LDAP attribute read | cn | 1 | Engineering Wiki (Confluence DC)
LDAP attribute read | department | 1 | Engineering Wiki (Confluence DC)
LDAP attribute read | employeeID | 1 | HR Analytics (Tableau)
LDAP attribute read | givenName | 2 | Engineering Wiki (Confluence DC), HR Analytics (Tableau)
LDAP attribute read | mail | 5 | Engineering Wiki (Confluence DC), Expense Portal, Expense Portal (UAT), HR Analytics (Tableau), Legacy Travel Booking
LDAP attribute read | sn | 2 | Engineering Wiki (Confluence DC), HR Analytics (Tableau)
LDAP attribute read | userPrincipalName | 2 | Engineering Wiki (Confluence DC), HR Analytics (Tableau)
Value with no directory source | appuser.costCenter | 1 | HR Analytics (Tableau)
Value with no directory source | user.id | 1 | Legacy Travel Booking

## Action plan
Application | When | Owner | Action | Resolves findings | Source | Review
Engineering Wiki (Confluence DC) | Before Migration | Directory Team | Pre-compute the expression result into a directory attribute, or get security approval for OGNL. | CLAIM_NEEDS_OGNL | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Add every ACS URL to the SP connection with the same index values. | MULTIPLE_ACS | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Enable 'Always sign the SAML assertion' on the SP connection. | RESPONSE_AND_ASSERTION_SIGNED | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Import the SP signing certificate into the connection. | SIGNED_AUTHN_REQUESTS | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Enable SLO on the SP connection and add the SP logout endpoint. | SLO_ENABLED | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | Directory Team | Store per-assignment values (e.g. role) in the directory or derive them from group membership. | ASSIGNMENT_PROFILE_ATTRIBUTES | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Set a virtual server ID matching the current issuer on the SP connection. | CUSTOM_IDP_ISSUER | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Configure a chained LDAP attribute source for group names and fulfil the group attribute from it. | GROUP_CLAIM | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | App Owner | Decide whether the Okta-only groups in the group claim must be created in the directory. | GROUP_CLAIM_OKTA_NATIVE_GROUPS | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
Engineering Wiki (Confluence DC) | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
Expense Portal | Before Migration | IAM Team | Enable 'Always sign the SAML assertion' on the SP connection. | RESPONSE_AND_ASSERTION_SIGNED | offline (offline-rules-v1) | PENDING
Expense Portal | Before Migration | App Owner | Decide how to separate apps sharing this SP entity ID (e.g. change the UAT entity ID on the SP). | DUPLICATE_SP_ENTITY_ID | offline (offline-rules-v1) | PENDING
Expense Portal | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
Expense Portal | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
Expense Portal | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | Before Migration | IAM Team | Enable 'Always sign the SAML assertion' on the SP connection. | RESPONSE_AND_ASSERTION_SIGNED | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | Before Migration | App Owner | Decide how to separate apps sharing this SP entity ID (e.g. change the UAT entity ID on the SP). | DUPLICATE_SP_ENTITY_ID | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | Before Migration | Directory Team | Create the Okta-only assigned groups in the directory and populate their members. | OKTA_NATIVE_GROUPS_ASSIGNED | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
Expense Portal (UAT) | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | Directory Team | Pre-compute the expression result into a directory attribute, or get security approval for OGNL. | CLAIM_NEEDS_OGNL | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | IAM Team | Enable 'Always sign the SAML assertion' on the SP connection. | RESPONSE_AND_ASSERTION_SIGNED | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | Directory Team | Move the Okta app-user attribute values into a directory attribute. | APPUSER_ATTRIBUTE_CLAIM | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | Directory Team | Store per-assignment values (e.g. role) in the directory or derive them from group membership. | ASSIGNMENT_PROFILE_ATTRIBUTES | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | IAM Team | Schedule the cutover before the Okta certificate expires, or rotate it on Okta. | CERT_EXPIRING | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | Directory Team | Create a directory group for directly assigned users and use it in the issuance criteria. | DIRECT_USER_ASSIGNMENTS | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | Before Migration | Directory Team | Create the Okta-only assigned groups in the directory and populate their members. | OKTA_NATIVE_GROUPS_ASSIGNED | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
HR Analytics (Tableau) | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | Before Migration | App Owner | Confirm whether the app still works; an expired signing certificate suggests it is unused. | CERT_EXPIRED | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | Before Migration | App Owner | Copy Okta user ids into a directory attribute, or agree an account re-link with the vendor. | NAMEID_IS_OKTA_USER_ID | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | Before Migration | IAM Team | Enable 'Always sign the SAML assertion' on the SP connection. | RESPONSE_AND_ASSERTION_SIGNED | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | During Cutover | Vendor | Agree SHA-256 signing with the vendor at cutover. | SHA1_SIGNATURE | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | Before Migration | App Owner | Confirm with the owner whether the app can be decommissioned instead of migrated. | NO_ASSIGNMENTS | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
Legacy Travel Booking | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
Salesforce | Before Migration | Vendor | Obtain the SP metadata (entity ID, ACS URLs, expected attributes) from the vendor. | CATALOG_APP_PARTIAL_CONFIG | offline (offline-rules-v1) | PENDING
Salesforce | Before Migration | IAM Team | Reproduce the custom app username exactly (directory attribute or approved OGNL). | CUSTOM_APP_USERNAME | offline (offline-rules-v1) | PENDING
Salesforce | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
Salesforce | Before Migration | Directory Team | Create the Okta-only assigned groups in the directory and populate their members. | OKTA_NATIVE_GROUPS_ASSIGNED | offline (offline-rules-v1) | PENDING
Salesforce | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
Salesforce | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING
ServiceNow | Before Migration | Vendor | Obtain the SP metadata (entity ID, ACS URLs, expected attributes) from the vendor. | CATALOG_APP_PARTIAL_CONFIG | offline (offline-rules-v1) | PENDING
ServiceNow | Before Migration | IAM Team | Add issuance criteria on the SP connection restricting access to the assigned groups (memberOf). | ISSUANCE_CRITERIA_REQUIRED | offline (offline-rules-v1) | PENDING
ServiceNow | Before Migration | Directory Team | Create the Okta-only assigned groups in the directory and populate their members. | OKTA_NATIVE_GROUPS_ASSIGNED | offline (offline-rules-v1) | PENDING
ServiceNow | During Cutover | Vendor | Give the SP the PingFederate metadata (entity ID, SSO URL, signing certificate) at cutover. | ' | offline (offline-rules-v1) | PENDING
ServiceNow | After Cutover | IAM Team | Test sign-in with pilot users, compare the assertion with Okta's, then remove the Okta app. | ' | offline (offline-rules-v1) | PENDING

## Owner questions
Application | Business owner | Question | Answer (fill in)
Engineering Wiki (Confluence DC) | Unknown | Who is the business owner for this application? | '
Engineering Wiki (Confluence DC) | Unknown | How critical is this application to the business (low / medium / high)? | '
Engineering Wiki (Confluence DC) | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Engineering Wiki (Confluence DC) | Unknown | Does the application need nested group membership or only direct groups? | '
Expense Portal | Unknown | Who is the business owner for this application? | '
Expense Portal | Unknown | How critical is this application to the business (low / medium / high)? | '
Expense Portal | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Expense Portal | Unknown | Can the non-production instance use a different SP entity ID? | '
Expense Portal (UAT) | Unknown | Who is the business owner for this application? | '
Expense Portal (UAT) | Unknown | How critical is this application to the business (low / medium / high)? | '
Expense Portal (UAT) | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Expense Portal (UAT) | Unknown | Can the non-production instance use a different SP entity ID? | '
HR Analytics (Tableau) | Unknown | Who is the business owner for this application? | '
HR Analytics (Tableau) | Unknown | How critical is this application to the business (low / medium / high)? | '
HR Analytics (Tableau) | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Legacy Travel Booking | Unknown | Who is the business owner for this application? | '
Legacy Travel Booking | Unknown | How critical is this application to the business (low / medium / high)? | '
Legacy Travel Booking | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Salesforce | Unknown | Who is the business owner for this application? | '
Salesforce | Unknown | How critical is this application to the business (low / medium / high)? | '
Salesforce | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
Salesforce | Unknown | Can you provide the SP SAML metadata or the vendor's SSO configuration page? | '
ServiceNow | Unknown | Who is the business owner for this application? | '
ServiceNow | Unknown | How critical is this application to the business (low / medium / high)? | '
ServiceNow | Unknown | Does the vendor provide a test or sandbox instance we can federate first? | '
ServiceNow | Unknown | Can you provide the SP SAML metadata or the vendor's SSO configuration page? | '

## Findings
Application | Severity | Code | Message
Employee Portal | WARNING | OIDC_ACCESS_CONTROL_REQUIRED | Okta only issues tokens to assigned users. In PingFederate, restrict this OAuth client with an authentication policy or issuance criteria on group membership, otherwise any user who can sign in gets tokens.
Employee Portal | WARNING | OIDC_NEW_CLIENT_SECRET | Confidential client using a shared secret. Okta does not hand back existing secrets, so plan a new secret in PingFederate and a coordinated update in the app.
Employee Portal | INFO | DIRECTORY_SOURCED_GROUPS_ASSIGNED | 1 assigned group(s) come from the directory, so PingFederate can check them through its LDAP data store.
Employee Portal | INFO | OIDC_ISSUER_CHANGE | Tokens will be issued by PingFederate, so the issuer, discovery URL and JWKS change. The app must point at PingFederate's /.well-known/openid-configuration at cutover.
Employee Portal | INFO | OIDC_REFRESH_TOKENS | The app uses refresh tokens. Okta refresh tokens cannot be moved, so users sign in again once after cutover.
Employee Portal | INFO | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | Scopes, custom claims and access policies live on the Okta authorization server and are not analysed yet (next sprint). Review them manually for now.
Engineering Wiki (Confluence DC) | CRITICAL | CLAIM_NEEDS_OGNL | Claim 'fullName': OGNL needed (<concatenation>); LDAP inputs: givenName, sn. OGNL is not allowed here, so the value must be pre-computed into a directory attribute.
Engineering Wiki (Confluence DC) | CRITICAL | CLAIM_NEEDS_OGNL | Claim 'wikiRole': OGNL needed (<conditional>); LDAP inputs: department. OGNL is not allowed here, so the value must be pre-computed into a directory attribute.
Engineering Wiki (Confluence DC) | WARNING | ASSIGNMENT_PROFILE_ATTRIBUTES | Assignments carry app-specific values (e.g. a role per group). PingFederate has nowhere to hold these; store them in the directory or derive them from group membership.
Engineering Wiki (Confluence DC) | WARNING | CUSTOM_IDP_ISSUER | The SP expects the custom issuer 'https://sso.northwind.example/wiki'. Either set a matching virtual server ID on the PingFederate connection or change the issuer on the SP.
Engineering Wiki (Confluence DC) | WARNING | GROUP_CLAIM | Group claim 'groups' (REGEX 'ENG-.*') matches 4 tenant group(s). Chained LDAP attribute source returning cn, e.g. (&(objectClass=group)(member=<user DN>)(cn=ENG-*)). Check whether the SP expects nested group membership.
Engineering Wiki (Confluence DC) | WARNING | GROUP_CLAIM_OKTA_NATIVE_GROUPS | Group claim 'groups' includes 1 Okta-only group(s) that PingFederate cannot see: ENG-Contractors. Create them in the directory or accept that they drop out of the assertion.
Engineering Wiki (Confluence DC) | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
Engineering Wiki (Confluence DC) | INFO | DEFAULT_RELAY_STATE | A default RelayState is set. Use it as the TargetResource for IdP-initiated SSO links.
Engineering Wiki (Confluence DC) | INFO | DIRECTORY_SOURCED_GROUPS_ASSIGNED | 3 assigned group(s) come from the directory, so PingFederate can check them through its LDAP data store.
Engineering Wiki (Confluence DC) | INFO | MULTIPLE_ACS | 2 ACS endpoints. Add each to the SP connection with the same index.
Engineering Wiki (Confluence DC) | INFO | RESPONSE_AND_ASSERTION_SIGNED | Okta signs both response and assertion. Enable 'Always sign the SAML assertion' on the SP connection so the SP still gets a signed assertion.
Engineering Wiki (Confluence DC) | INFO | SIGNED_AUTHN_REQUESTS | The SP signs AuthnRequests. Import its signing certificate into the SP connection.
Engineering Wiki (Confluence DC) | INFO | SLO_ENABLED | Single logout is enabled. Enable SLO on the SP connection and add the SP's SLO endpoint.
Expense Portal | WARNING | DUPLICATE_SP_ENTITY_ID | SP entity ID 'https://expenses.northwind.example' is also used by: Expense Portal (UAT). PingFederate identifies each SP connection by its partner entity ID, so these cannot be separate connections as-is.
Expense Portal | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
Expense Portal | INFO | DIRECTORY_SOURCED_GROUPS_ASSIGNED | 1 assigned group(s) come from the directory, so PingFederate can check them through its LDAP data store.
Expense Portal | INFO | RESPONSE_AND_ASSERTION_SIGNED | Okta signs both response and assertion. Enable 'Always sign the SAML assertion' on the SP connection so the SP still gets a signed assertion.
Expense Portal (UAT) | WARNING | DUPLICATE_SP_ENTITY_ID | SP entity ID 'https://expenses.northwind.example' is also used by: Expense Portal. PingFederate identifies each SP connection by its partner entity ID, so these cannot be separate connections as-is.
Expense Portal (UAT) | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
Expense Portal (UAT) | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 1 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.
Expense Portal (UAT) | WARNING | UNUSED_IN_WINDOW | No successful sign-ins in the last 90 days although 5 user(s) are assigned. Strong decommission candidate: confirm with the owner before migrating.
Expense Portal (UAT) | INFO | RESPONSE_AND_ASSERTION_SIGNED | Okta signs both response and assertion. Enable 'Always sign the SAML assertion' on the SP connection so the SP still gets a signed assertion.
HR Analytics (Tableau) | CRITICAL | CLAIM_NEEDS_OGNL | Claim 'displayName': OGNL needed (<concatenation>); LDAP inputs: givenName, sn. OGNL is not allowed here, so the value must be pre-computed into a directory attribute.
HR Analytics (Tableau) | CRITICAL | CLAIM_NEEDS_OGNL | Claim 'username': OGNL needed (String.substringBefore); LDAP inputs: userPrincipalName. OGNL is not allowed here, so the value must be pre-computed into a directory attribute.
HR Analytics (Tableau) | WARNING | APPUSER_ATTRIBUTE_CLAIM | Claim 'costCenter' reads an Okta app-user attribute. Store the value in the directory (or derive it from groups) so PingFederate has a source.
HR Analytics (Tableau) | WARNING | ASSIGNMENT_PROFILE_ATTRIBUTES | Assignments carry app-specific values (e.g. a role per group). PingFederate has nowhere to hold these; store them in the directory or derive them from group membership.
HR Analytics (Tableau) | WARNING | CERT_EXPIRING | Active signing certificate expires in 44 days (2026-11-11). Migrating before expiry avoids a rotation on Okta.
HR Analytics (Tableau) | WARNING | DIRECT_USER_ASSIGNMENTS | 2 user(s) are assigned directly. PingFederate has no per-user app assignment; put these users in a directory group and use it in issuance criteria.
HR Analytics (Tableau) | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
HR Analytics (Tableau) | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 1 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.
HR Analytics (Tableau) | INFO | RESPONSE_AND_ASSERTION_SIGNED | Okta signs both response and assertion. Enable 'Always sign the SAML assertion' on the SP connection so the SP still gets a signed assertion.
Legacy Intranet SPA | WARNING | DIRECT_USER_ASSIGNMENTS | 1 user(s) are assigned directly. PingFederate has no per-user app assignment; put these users in a directory group and use it in issuance criteria.
Legacy Intranet SPA | WARNING | OIDC_ACCESS_CONTROL_REQUIRED | Okta only issues tokens to assigned users. In PingFederate, restrict this OAuth client with an authentication policy or issuance criteria on group membership, otherwise any user who can sign in gets tokens.
Legacy Intranet SPA | WARNING | OIDC_IMPLICIT_GRANT | Implicit grant is enabled. It is deprecated; use the move to switch the app to authorization code with PKCE.
Legacy Intranet SPA | WARNING | OIDC_WILDCARD_REDIRECT | Wildcard redirect URIs are used. Confirm PingFederate's redirect URI matching will accept the same values, or list them explicitly.
Legacy Intranet SPA | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 1 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.
Legacy Intranet SPA | WARNING | UNUSED_IN_WINDOW | No successful sign-ins in the last 90 days although 9 user(s) are assigned. Strong decommission candidate: confirm with the owner before migrating.
Legacy Intranet SPA | INFO | OIDC_ISSUER_CHANGE | Tokens will be issued by PingFederate, so the issuer, discovery URL and JWKS change. The app must point at PingFederate's /.well-known/openid-configuration at cutover.
Legacy Intranet SPA | INFO | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | Scopes, custom claims and access policies live on the Okta authorization server and are not analysed yet (next sprint). Review them manually for now.
Legacy Travel Booking | CRITICAL | CERT_EXPIRED | Active signing certificate expired on 2026-03-01.
Legacy Travel Booking | CRITICAL | NAMEID_IS_OKTA_USER_ID | NameID is the Okta user id. PingFederate can only emit it if the id is copied into a directory attribute before cutover; otherwise the SP must re-link accounts.
Legacy Travel Booking | WARNING | NO_ASSIGNMENTS | No users or groups are assigned. Likely a decommission candidate rather than a migration.
Legacy Travel Booking | INFO | APP_INACTIVE | App is INACTIVE in Okta. Confirm with the owner whether to migrate or decommission.
Legacy Travel Booking | INFO | RESPONSE_AND_ASSERTION_SIGNED | Okta signs both response and assertion. Enable 'Always sign the SAML assertion' on the SP connection so the SP still gets a signed assertion.
Legacy Travel Booking | INFO | SHA1_SIGNATURE | SHA-1 signing is used. Agree a move to SHA-256 with the vendor at cutover.
Mobile Expenses | WARNING | OIDC_ACCESS_CONTROL_REQUIRED | Okta only issues tokens to assigned users. In PingFederate, restrict this OAuth client with an authentication policy or issuance criteria on group membership, otherwise any user who can sign in gets tokens.
Mobile Expenses | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 1 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.
Mobile Expenses | INFO | OIDC_ISSUER_CHANGE | Tokens will be issued by PingFederate, so the issuer, discovery URL and JWKS change. The app must point at PingFederate's /.well-known/openid-configuration at cutover.
Mobile Expenses | INFO | OIDC_REFRESH_TOKENS | The app uses refresh tokens. Okta refresh tokens cannot be moved, so users sign in again once after cutover.
Mobile Expenses | INFO | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | Scopes, custom claims and access policies live on the Okta authorization server and are not analysed yet (next sprint). Review them manually for now.
Reporting API | INFO | OIDC_ISSUER_CHANGE | Tokens will be issued by PingFederate, so the issuer, discovery URL and JWKS change. The app must point at PingFederate's /.well-known/openid-configuration at cutover.
Reporting API | INFO | OIDC_MACHINE_CLIENT | Machine-to-machine client (client_credentials): no users are assigned by design. Identify the calling system's owner and the APIs (scopes) it needs.
Reporting API | INFO | OIDC_PRIVATE_KEY_JWT | The client authenticates with private_key_jwt. Register its public key (JWKS) on the PingFederate client; no secret needs to change.
Reporting API | INFO | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | Scopes, custom claims and access policies live on the Okta authorization server and are not analysed yet (next sprint). Review them manually for now.
Salesforce | WARNING | CATALOG_APP_PARTIAL_CONFIG | OIN catalog app ('salesforce'). Okta's API does not return the SP's ACS URL, entity ID or built-in claims. Get the SP metadata from the vendor; PingFederate can import it when creating the SP connection.
Salesforce | WARNING | CUSTOM_APP_USERNAME | Custom Okta app username '${source.employeeNumber}@northwind.sfdc'. The SP likely keys accounts on it; PingFederate must produce the identical value (OGNL or a directory attribute).
Salesforce | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
Salesforce | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 1 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.
ServiceNow | WARNING | CATALOG_APP_PARTIAL_CONFIG | OIN catalog app ('servicenow_ud'). Okta's API does not return the SP's ACS URL, entity ID or built-in claims. Get the SP metadata from the vendor; PingFederate can import it when creating the SP connection.
ServiceNow | WARNING | ISSUANCE_CRITERIA_REQUIRED | Okta limits this app to assigned users. PingFederate has no app assignments, so without issuance criteria (or an authentication policy rule) on the SP connection, any user who can sign in gets an assertion. Restrict on group membership.
ServiceNow | WARNING | OKTA_NATIVE_GROUPS_ASSIGNED | 2 assigned group(s) exist only in Okta. Create and populate them in the directory before the issuance criteria can use them.

## Risk breakdown
Application | Dimension | Rule | Points | Reason | Rules version
Employee Portal | COMPLEXITY | OIDC_ACCESS_CONTROL_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Employee Portal | COMPLEXITY | OIDC_NEW_CLIENT_SECRET | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Employee Portal | COMPLEXITY | OIDC_REFRESH_TOKENS | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Employee Portal | COMPLEXITY | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Employee Portal | IMPACT | ACTIVE_USERS | 1 | 24 active users in 90 days (25 assigned) | 2026.09-pf-2
Employee Portal | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Employee Portal | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | ASSIGNMENT_PROFILE_ATTRIBUTES | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | CLAIM_NEEDS_OGNL | 6 | 2 occurrence(s) x 3 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | CUSTOM_IDP_ISSUER | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | GROUP_CLAIM | 3 | 1 occurrence(s) x 3 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | GROUP_CLAIM_OKTA_NATIVE_GROUPS | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | MULTIPLE_ACS | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | SIGNED_AUTHN_REQUESTS | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | COMPLEXITY | SLO_ENABLED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Engineering Wiki (Confluence DC) | IMPACT | ACTIVE_USERS | 1 | 9 active users in 90 days (10 assigned) | 2026.09-pf-2
Engineering Wiki (Confluence DC) | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Engineering Wiki (Confluence DC) | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Expense Portal | COMPLEXITY | DUPLICATE_SP_ENTITY_ID | 3 | 1 occurrence(s) x 3 | 2026.09-pf-2
Expense Portal | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Expense Portal | IMPACT | ACTIVE_USERS | 1 | 22 active users in 90 days (25 assigned) | 2026.09-pf-2
Expense Portal | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Expense Portal | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Expense Portal (UAT) | COMPLEXITY | DUPLICATE_SP_ENTITY_ID | 3 | 1 occurrence(s) x 3 | 2026.09-pf-2
Expense Portal (UAT) | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Expense Portal (UAT) | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Expense Portal (UAT) | IMPACT | ACTIVE_USERS | 0 | 0 active users in 90 days (5 assigned) | 2026.09-pf-2
Expense Portal (UAT) | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Expense Portal (UAT) | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | APPUSER_ATTRIBUTE_CLAIM | 3 | 1 occurrence(s) x 3 | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | ASSIGNMENT_PROFILE_ATTRIBUTES | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | CLAIM_NEEDS_OGNL | 6 | 2 occurrence(s) x 3 | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | DIRECT_USER_ASSIGNMENTS | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
HR Analytics (Tableau) | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
HR Analytics (Tableau) | IMPACT | ACTIVE_USERS | 1 | 4 active users in 90 days (5 assigned) | 2026.09-pf-2
HR Analytics (Tableau) | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
HR Analytics (Tableau) | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | DIRECT_USER_ASSIGNMENTS | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | OIDC_ACCESS_CONTROL_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | OIDC_IMPLICIT_GRANT | 3 | 1 occurrence(s) x 3 | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | OIDC_WILDCARD_REDIRECT | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Legacy Intranet SPA | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Legacy Intranet SPA | IMPACT | ACTIVE_USERS | 0 | 0 active users in 90 days (9 assigned) | 2026.09-pf-2
Legacy Intranet SPA | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Legacy Intranet SPA | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Legacy Travel Booking | COMPLEXITY | NAMEID_IS_OKTA_USER_ID | 5 | 1 occurrence(s) x 5 | 2026.09-pf-2
Legacy Travel Booking | IMPACT | APP_INACTIVE | 0 | Inactive in Okta: no live users affected | 2026.09-pf-2
Mobile Expenses | COMPLEXITY | OIDC_ACCESS_CONTROL_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Mobile Expenses | COMPLEXITY | OIDC_REFRESH_TOKENS | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Mobile Expenses | COMPLEXITY | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Mobile Expenses | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Mobile Expenses | IMPACT | ACTIVE_USERS | 1 | 4 active users in 90 days (5 assigned) | 2026.09-pf-2
Mobile Expenses | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Mobile Expenses | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Reporting API | COMPLEXITY | OIDC_SCOPES_CLAIMS_NOT_ANALYSED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Reporting API | IMPACT | ACTIVE_USERS | 0 | 0 active users in 90 days (0 assigned) | 2026.09-pf-2
Reporting API | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Reporting API | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
Salesforce | COMPLEXITY | CATALOG_APP_PARTIAL_CONFIG | 5 | 1 occurrence(s) x 5 | 2026.09-pf-2
Salesforce | COMPLEXITY | CUSTOM_APP_USERNAME | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Salesforce | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
Salesforce | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
Salesforce | IMPACT | ACTIVE_USERS | 1 | 7 active users in 90 days (8 assigned) | 2026.09-pf-2
Salesforce | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
Salesforce | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2
ServiceNow | COMPLEXITY | CATALOG_APP_PARTIAL_CONFIG | 5 | 1 occurrence(s) x 5 | 2026.09-pf-2
ServiceNow | COMPLEXITY | ISSUANCE_CRITERIA_REQUIRED | 1 | 1 occurrence(s) x 1 | 2026.09-pf-2
ServiceNow | COMPLEXITY | OKTA_NATIVE_GROUPS_ASSIGNED | 2 | 1 occurrence(s) x 2 | 2026.09-pf-2
ServiceNow | IMPACT | ACTIVE_USERS | 1 | 12 active users in 90 days (12 assigned) | 2026.09-pf-2
ServiceNow | IMPACT | BUSINESS_CRITICALITY | 2 | Criticality not captured (assumed MEDIUM) | 2026.09-pf-2
ServiceNow | IMPACT | TEST_ENVIRONMENT | 2 | Test environment not captured | 2026.09-pf-2