# Okta to PingFederate migration strategy

Customer · generated 27 Sep 2026

# Executive summary

Customer has 13 applications in Okta, of which 11 use SAML or OIDC and are in scope for PingFederate. 3 of these look unused or retired and should be decommissioned rather than migrated, leaving 8 applications used by about 82 people. With the current assumptions the migration runs from 28 Sep 2026 to 15 Nov 2026 in 3 wave(s), for roughly 116 hours of engineering effort.

3 application(s) are blocked until 3 decision(s) are made; the most valuable is "Allow OGNL expressions in PingFederate?" (2 app(s)).

Start with Wave 1 (4 app(s), cutover around 18 Oct).

The directory needs 6 group(s) and 1 attribute value(s) before the affected apps can move.

Agree the open decisions in the next steering meeting, confirm owners and test environments for the first wave, and start directory preparation in parallel.

# Scope

|  | Applications |
| --- | --- |
| In Okta | 13 |
| SAML | 7 |
| OIDC | 4 |
| Other (bookmark, password vaulting…) - out of scope | 2 |
| Decommission candidates | 3 |
| To migrate | 8 |
| People affected (active users where known) | 82 |

Decommission candidates: Expense Portal (UAT), Legacy Intranet SPA, Legacy Travel Booking

# Approach

Migrate in waves: a low-risk pilot wave first, high-impact apps last, blocked apps after their decisions are made.

Keep each Okta app active until its PingFederate connection is verified in production, so rollback is a single SP-side change.

Recreate access control explicitly: PingFederate has no app assignments, so every app gets issuance criteria or an access policy.

Prepare the directory first (Okta-only groups, app-specific attributes), because PingFederate reads users and groups from it.

Coordinate SP-side changes early: each vendor or app team must accept PingFederate's metadata, certificate and endpoints.

Decommission instead of migrating where apps are unused, unassigned or inactive.

# Waves and timeline

| Wave | Apps | Users | Effort (h) | Planned cutover |
| --- | --- | --- | --- | --- |
| Wave 1 | Employee Portal, Mobile Expenses, Reporting API, ServiceNow | 40 | 39.6 | 18 Oct 2026 |
| Wave 2 | Salesforce | 7 | 14.4 | 25 Oct 2026 |
| Blocked | Engineering Wiki (Confluence DC), Expense Portal, HR Analytics (Tableau) | 35 | 51.6 | 08 Nov 2026 |

Assumptions: start 28 Sep 2026; 2 engineer(s) at 30 h/week; vendor lead time 14 days; pilot 5 days; hypercare 7 days; decisions within 21 days; 20% buffer. Calendar days. Total effort about 116 hours, finishing around 15 Nov 2026.

| Wave | Phase | Start | End |
| --- | --- | --- | --- |
| All waves | Directory prep | 28 Sep | 05 Oct |
| Wave 1 | Build in PingFederate | 28 Sep | 05 Oct |
| Wave 1 | SP / app changes (vendor lead time) | 28 Sep | 12 Oct |
| Wave 1 | Pilot | 12 Oct | 17 Oct |
| Wave 1 | Cutover | 17 Oct | 18 Oct |
| Wave 1 | Hypercare, then remove from Okta | 18 Oct | 25 Oct |
| Wave 2 | Build in PingFederate | 05 Oct | 12 Oct |
| Wave 2 | SP / app changes (vendor lead time) | 05 Oct | 19 Oct |
| Wave 2 | Pilot | 19 Oct | 24 Oct |
| Wave 2 | Cutover | 24 Oct | 25 Oct |
| Wave 2 | Hypercare, then remove from Okta | 25 Oct | 01 Nov |
| Blocked | Decisions | 28 Sep | 19 Oct |
| Blocked | Build in PingFederate | 19 Oct | 26 Oct |
| Blocked | SP / app changes (vendor lead time) | 19 Oct | 02 Nov |
| Blocked | Pilot | 02 Nov | 07 Nov |
| Blocked | Cutover | 07 Nov | 08 Nov |
| Blocked | Hypercare, then remove from Okta | 08 Nov | 15 Nov |

# Decisions needed

| Decision | Apps affected | Unblocks | Owner | Options |
| --- | --- | --- | --- | --- |
| Allow OGNL expressions in PingFederate? | 2 | 2 | Security + IAM lead | Allow OGNL (reviewed, documented expressions) / No OGNL: pre-compute values in the directory |
| How to handle apps that share one SP entity ID? | 2 | 2 | App owners | Change the non-production SP's entity ID / Decommission the duplicate (e.g. unused UAT) / Use one connection for both |
| Apps keyed on the Okta user ID: copy IDs or re-link? | 1 | 1 | IAM lead + App owner | Copy Okta user IDs into a directory attribute / Vendor re-links accounts / Decommission the app |
| Okta-only groups: recreate in the directory or replace? | 7 | 0 | Directory team | Create in the directory and sync membership / Replace with existing directory groups |
| Decommission unused / unassigned apps instead of migrating? | 3 | 0 | Service owner | Decommission after owner confirmation / Migrate anyway |
| Where do app-specific attributes live after Okta? | 2 | 0 | Directory team | Directory attributes (e.g. extensionAttributeN) / Derive from group membership |
| Move implicit-grant OIDC apps to code + PKCE during migration? | 1 | 0 | App owners | Yes, modernise during migration / No, keep implicit for now |
| How are new OIDC client secrets delivered to app teams? | 1 | 0 | Security | Secrets vault hand-off / Direct secure hand-off at cutover |

# Key risks

| Risk | Severity | Applications |
| --- | --- | --- |
| Claim Needs Ognl | Critical | Engineering Wiki (Confluence DC), HR Analytics (Tableau) |
| SP settings not visible in Okta (catalog apps): vendor metadata needed | Warning | ServiceNow, Salesforce |

# Directory preparation

6 Okta-only group(s) to create, 1 value(s) with no directory source.

| Group | Used by |
| --- | --- |
| ENG-Contractors | Engineering Wiki (Confluence DC) |
| Finance | Mobile Expenses |
| HR-Analysts | HR Analytics (Tableau) |
| SN-Approvers | ServiceNow |
| SN-ITIL | ServiceNow |
| Sales | Salesforce |

| Okta value | Used by |
| --- | --- |
| appuser.costCenter | HR Analytics (Tableau) |

# Next steps (two weeks)

Decide: Allow OGNL expressions in PingFederate? (owner: Security + IAM lead; affects 2 app(s)).

Decide: How to handle apps that share one SP entity ID? (owner: App owners; affects 2 app(s)).

Decide: Apps keyed on the Okta user ID: copy IDs or re-link? (owner: IAM lead + App owner; affects 1 app(s)).

Confirm decommissioning with owners of: Expense Portal (UAT), Legacy Intranet SPA, Legacy Travel Booking.

Send the app-owner pack for Wave 1 and book pilot users and change windows.

Directory team: create 6 group(s) and add missing attributes.

Request SP metadata from vendors of: ServiceNow, Salesforce.

Export the PingFederate build package for the first wave and review it with the PingFederate admins.

Figures come from automated discovery of Okta and deterministic rules; dates are planning estimates based on the stated assumptions.